## Sheet1
| Time estimate (shirt size) | Start date | Actual time spent
Time Estimates & Daily Task Sheet | small | 2025-05-08 | >1 day
Use Case Diagram | medium | 2025-05-08 | 1 day
Sequence Diagram for web and iOS | medium | 2025-05-08 | 1.5 days
Object Model | medium | 2025-05-08 | 1 day
Design the Application in Figma | small | 2025-05-08 | 1 day
Smart Contract | large | 2025-05-14 | 2 days
Hardhat Created and Contract Added | large | 2025-05-14 | 2 days
Git Repository for Project | small | 2025-05-08 | >1 day
NextJS Connect to Wallet | medium | 2025-05-14 | 1.5 days
NextJS Call Contract Function | medium | 2025-05-14 | 2 days
Design and Implement SQL Database | XL | 2025-05-12 | 4 days
Express get route | large | 2025-05-12 | 3 days
CSS in NextJS | small | 2025-05-13 | >1 day
Reusable Component | medium | 2025-05-12 | 2 days
NextJS Connection to Express Route | Large | 2025-05-12 | 3 days
iOS Fetch from Express Server | Large | 2025-05-12 | 2 days
Commenting in Code | Small | 2025-05-08 | >1 day
Folder Management | Small | 2025-05-08 | >1 day
Reflection Paper on Project | Small | 2025-05-14 | >1 day
Presentation Video | Small | 2025-05-14 | >1 day
The equation | Start date - end date